APT Alternate Parts Monitoring – Solution Plan

Prepared by: Shivam Jha | Date: Nov 05, 2025

1. Executive Summary

The Alternates Part Team (APT) currently operates an Excel-based tracker for Shortages, Problem Reports (PRs), and Deviations tied to Alternate Part reason codes. This results in heavy manual work, errors, and a lack of auditability. This plan proposes a full-code, LAM-compliant, database-backed web application that becomes the single source of truth, automates ingestion from source systems/CSV drops, enforces validations and audit history, and provides in-app reporting—eliminating ≥50% manual effort and saving ~300 hours annually.

2. Problem Statement

There is no reliable, controlled system to monitor APT Problem Reports for Alternate Part reason codes. Current Excel-based processes are manual, prone to data mismatches/crashes, and provide no audit trail.

3. Objectives

Replace Excel-based manual entry with a controlled, auditable system.

Store and monitor Shortages, PRs, and Deviations for Alternate Part reason codes.

Automate ingestion from ERP/PLM or CSV drops with validations and deduplication.

Provide in-app dashboards and exports (no Power BI/Power Automate).

Achieve ≥50% manual effort reduction and ~300 hours/year saved.

Ensure LAM compliance: RBAC, audit trails, UAT evidence, and release controls.

4. Scope

4.1 In Scope

Data model for Parts, ProblemReports, Shortages, Deviations, and Status History.

ASP.NET Core REST API with validation and status transition rules.

Background ingestion worker for CSV/XLSX (file-based MVP).

React + TypeScript web UI for search, filters, updates, and basic charts.

RBAC-ready integration with Microsoft Entra ID (phased).

Audit logging via append-only status history and DB constraints.

4.2 Out of Scope (v1)

Power BI/Power Automate components.

Direct ERP/PLM real-time integrations (will use scheduled exports in MVP).

Complex approval workflows beyond deviation approval (basic flow only).

Advanced S&OP analytics (v2).

5. Current Pain Points (Today)

Manual Excel updates → high error risk and inconsistent versions.

No audit trail for who changed what/when.

Slow, manual monitoring and reporting.

Excel crashes and file corruption risks.

6. Proposed Solution Overview

A full-code system with a normalized SQL database, a secure REST API, a background ingestion worker, and a React UI. All writes occur through the API or controlled ingestion. The system enforces validations, maintains immutable status history, and provides role-based access and in-app KPIs.

6.1 Architecture (High Level)

• Backend: ASP.NET Core 8 (REST), EF Core 9, SQL Server (Azure SQL-ready).
• Ingestion: .NET background worker parsing CSV/XLSX from a secure drop (SharePoint/Blob).
• Frontend: React + TypeScript + Vite with TanStack Query.
• AuthN/Z (v2): Microsoft Entra ID (JWT), role claims for RBAC.
• Hosting: Azure App Service/Container Apps (API & Worker), Azure SQL (DB).

6.2 Data Model (Core Entities)

Parts: PartNumber, Description, Plant, IsAlternatePart, LifecycleState.

ProblemReports: PartId, ReasonCode, Status, Priority, OwnerUpn, OpenedDate, ClosedDate, SlaDue.

PRStatusHistory: OldStatus, NewStatus, ChangedByUpn, ChangedAt, Comments (append-only).

Shortages: PartId, Date, QtyRequired, QtyOnHand, CoverageDays, DemandRef.

Deviations: PartId, ProblemReportId?, Type, EffectiveFrom, EffectiveTo?, ApprovedByUpn.

6.3 Key Behaviors & Controls

Status transition rules (e.g., New → InAnalysis → AwaitingDeviation → Approved → Implemented → Closed).

Validation: required fields, reason code whitelist, duplicate checks (e.g., PR_SourceId).

Audit: auto-write to PRStatusHistory on any status change.

RBAC: Owner/Editor/Viewer roles; plant-level scoping (v2).

Exports: read-only CSV/XLSX for legacy consumers.

7. Non-Functional Requirements

Availability: 99.5%+ in business hours (define with business).

Performance: list views <2s for 5–10k rows (server-side paging & indexes).

Security: Entra ID SSO, least-privilege RBAC, encrypted at rest/in transit.

Audit & Compliance: complete history of status changes and administrative actions.

Backup & DR: automated daily backups; restore test per quarter.

8. Implementation Plan & Milestones

| Milestone | Description | Owner | Target |
| --- | --- | --- | --- |
| Problem Statement | Confirm problem, objectives, KPIs, stakeholders. | APT + Business | Week 1 |
| Data Pull & Analysis | Field mapping, reason codes, data quality checks. | Analytics + APT | Week 1–2 |
| Process Review | Define PR lifecycle, SLAs, roles, approvals. | APT Leads | Week 2 |
| Work Instruction (WI) | Draft user flows, responsibilities, audit needs. | APT + QA | Week 2–3 |
| OES/IT Ticket | Create request with scope, security, environments. | APT | Week 2 |
| Build (API/DB) | Schema, EF, REST endpoints, auth scaffolding. | Engineering | Week 3–4 |
| Build (UI) | React pages, filters, status update, KPIs. | Engineering | Week 4–5 |
| Ingestion Worker | CSV/XLSX parser, validation, upsert, logs. | Engineering | Week 4–5 |
| UAT | Parallel run vs Excel, reconcile and fix gaps. | APT + Business | Week 6 |
| Release & Training | Cutover, training, hypercare. | APT + Eng | Week 7 |

9. RACI (High-Level)

| Activity | R (Responsible) | A (Accountable) | C (Consulted) | I (Informed) |
| --- | --- | --- | --- | --- |
| Requirements & WI | APT | Business Owner | Analytics, QA | Leadership |
| Data Sourcing | Analytics | IT/Analytics Lead | APT | Security |
| API & DB Dev | Engineering | Eng Lead | Analytics | APT |
| UI Dev | Engineering | Eng Lead | APT | Business |
| UAT | APT + Business | Business Owner | Engineering | Leadership |
| Release | Engineering | Business Owner | APT, QA | All |

10. Risks & Mitigations

| Risk | Mitigation | Owner |
| --- | --- | --- |
| Analytics prioritization delay | Deliver file-based ingest MVP; decouple API build from ERP integration. | Assigned |
| Access to source systems | Start with scheduled CSV exports; plan API connectors in v2. | Assigned |
| Change adoption | Keep Excel export read-only; provide quick filters and status updates in UI; training. | Assigned |
| Scope creep | Lock v1 scope to PR/Deviation/Shortage core; maintain backlog and change control. | Assigned |
| Security review timeline | Engage security early; document RBAC, audit, and data flows. | Assigned |

11. Success Criteria & KPIs

≥50% reduction in manual activity (measured by time-on-task & number of manual entries).

~300 hours/year saved (baseline vs. post-go-live activity logs).

≥3 stakeholder groups actively using the app weekly (adoption).

0 uncontrolled edits; 100% of status changes present in history (audit).

PR aging and SLA breach rate visible and trending down after 4–6 weeks.

12. UAT Plan (Monitoring & Validation)

Parallel run for 2–3 weeks with Excel tracker.

Data reconciliation: counts by status/reason/plant, sample records, and aging.

User scenarios: create/update PR, status transitions, deviation approval, exports.

Defect triage and fixes before go-live.

13. Cutover, Training & Support

Cutover window with short data freeze and final import.

Training: 30–45 min session + step-by-step WI with screenshots.

Hypercare: first 2 weeks post-go-live; daily triage window.

Support: ticketing via ITSM with clear ownership and SLAs.

14. Open Questions for Business Validation

What exactly does LAM entail in our org (gates, evidence, approvals)?

Which source systems are authoritative for parts/PRs/shortages? API access or file exports?

What is the official Reason Code list and which ones are considered 'Alternate Part'?

What SLA rules and aging buckets should we enforce and report?

Role model: who can create/update/approve? Any plant/supplier scoping?

Non-functional targets: availability, response time, data retention?

Preferred hosting & environments (Dev/Test/Prod) and go-live window?

Any regulatory or data classification constraints to document?

15. Next Steps

Review this plan with business and confirm scope, KPIs, and timeline.

Finalize data dictionary and field mappings with Analytics.

Spin up Dev environment (DB, API, Worker, UI) and start MVP build.

Prepare Work Instruction (WI) draft for UAT and training.